## Sheet1
No. | ODPC Recommendation | Controller Comment | Resultant Action | Owner
R-1 | Continuous monitoring and review to satisfying requirements of necessity and proportionality | Accept recommendation. Advisory Committee are committed via its TOR to put in place the necessary continuous review of the efficacy of the app to ensure that the processing of personal data by the app meet the requirements of necessity and proportionality. | Advisory Committee to put in place an evidence based efficacy review to support the Committee in carrying out its obligations in this regard. | App Advisory Committee
R-2 | Identify ownership of risks and their mitigation. Thorough testing and validation processes. Privacy by design and default. | Accept recommendation. Owners will be identified for each risk and their mitigation for ongoing review; Confirm that privacy by design and default has been a design principle from the start of the development of the app and will continue to be so - supporting documentation to be published; Significant security and validation testing has been performed during development phase, and this will continue for all subsquent updates as required; | Assign ownership for each risk for ongoing monitoring; Publish design and implementation measures, testing and security tests; | App Team
R-3 | Publish DPIA, source code and related documents (inc. joint controller arrangment). | Accept recommendation. Source code, DPIA and related documents are to be published as soon as possible | Publish source code, DPIA and related documents | App Team
R-4 | Data minimisation should be explained, in particular data anonymised by data controllers. Tranasparency of no linkages/cross-pollinatoin of personal data between app functions. | Accept recommendation. DPIA will be updated to explain anonymisation of data and risk of re-identification - additional appendix. DPIN will be updated to give clarity regarding no linkages/cross-pollination of personal data between functions. | Update DPIA and DPIN | App Team
R-5 | Publish results of testing and independent analysis. | Accept recommendation. Test results and independent analysis of functionality will be published. | Publish results of testing and any independent analysis | App Team / App Advisory Committee
R-6 | Set out justification for retention periods in DPIA and DPIN and measures to ensure retention policies are implemented. | Accept recommendations. DPIA and DPIN will be updated accordingly. | Update DPIA and DPIN | App Team
R-7 | Publish security testing analysis and results/thread model/relevant DPA elements | Accept recommendations. Will publish results and analysis of security testing and threat model, while ensuring the security of the app is not compromised. | Publish relevant documents | App Team
R-8 | Analysis of compliance with requirements of GDPR Article 7 on consent be published. | Accept recommendations. DPIA to be updated to include specific analysis on Article 7 GDPR. | Update DPIA | App Team
R-9 | Continuous stakeholder engagement for efficacy review; publish relevant feedback. | Accept recommendation. Ongoing stakeholder engagement is a charge of the Advisory Committee to oversee. Research related research and assessments will be published. | Ensure skakeholder engagement continues; and publish feedback. | App Team / App Advisory Committee
R-10 | Assessment of anonymity of data going from HSE to CSO. | Accept recommendation. Anonymity assessment details will be added to the DPIA; and DPIN ensure transparency in this regard | Update DPIA and DPIN | App Team
R-11 | Advisory Committee minutes to be made public including; including assessments provided to it. Independent verifcation of wind-down criteria and processes to be carried out. | Accept recommendation. Advisory Committee minutes and efficacy information/assessments will be published. Independent wind-down process will be validated. | Publish minutes and assessments of Advisory Committee; Carry out an independent review of the wind-down process and critera. | App Advisory Committee
R-12 | Clearly describe data subject rights to users, including relevant elements of joint contorller agreement in DPIN; put in place appropriate data protection policy to facilitate the exercise of these rights; ENS data clarity. | Accept recommendation. Data subject rights and their excercise will be clearly set out in the DPIN with regards data subject rights and the joint controller arrangement aspects that are relevant. The relevant data protection policies are in place to exercise data subject rights. | Update DPIN; Review App screens, in particular Leave screen re ENS clarity. | App Team
R-13 | Independent/Secondary review of testing of security measures where possible, and publication; consider data protection training for appropriate staff; ongoing review of organisational and technical measures in securing data. | Accept recommendation. Review of testing of security measures will be undertaken and publication of results. Data protection training is in place and will be emphasised for those involved in the app that are directly responsible for the processing of personal data. TORs for the App Advisory Committee to be updated. | Implement review of security testing and publish; Emphasise and facilitate DP course for relevant personnel; Update TORs of Committee | App Team / App Advisory Committee
R-14 | Continually review the appropriatness of using ENS, including reference to independent review | Accept recommendation. Testing of ENS is ongoing and stakeholder engagement in this area will continue | Continue to test ENS and engage with wider stakeholders in its use. | App Team